## Sheet1
| Tasks | GUI(hours) | Code(hours) | Note
IPHONE | Design | 8
| Login page | 4 | 8
| Register page | 4 | 8
| Main page | 4 | 16
| Search page | 4 | 10
| ToDo page | 4 | 12 | (todo list store on device)
| Feed page | 4 | 16
| Following/Follower list | 4 | 8
| Comments list page | 4 | 12
| Recipe page | 4 | 8
| Like function | 0 | 8
| Profile page | 4 | 12
| Ingredient page | 4 | 8
| Direction page | 4 | 16
| My Recipe page | 4 | 8
| Add Recipe page | 4 | 8
| Recipe Ingredient List | 4 | 10
| Add Ingredient Page | 4 | 10
XML SERVICE | Login service |  | 2
| Register service |  | 3
| Recipe service |  | 6
| Profile service |  | 6
| Comment service |  | 6
| Like service |  | 6
| Follow service |  | 8
| Feed Push Notification service |  | 20
| Ingredient service |  | 6
| Upload service |  | 6
| Saving ingredient from user |  | 3
| Store service |  | 6
| Add user recipe |  | 3
| Tracking service |  | 12
ADMIN | Database |  | 16
| Manage users |  | 2 | (list, add, update)
| Manage stores | 4 | 6 | (list, add, update)
| Manage recipe | 4 | 6 | (list, add, update)
| Manage ingredient | 4 | 6 | (list, add, update)
| Front-end CMS | 8 | 8
| Project Analytics |  | 10
| Sub Total (hours) | 92 | 325
| Total (hours) | 417
Note
VPS | HDD: 160GB
CPU: Sandy Bridge 3.2Ghz
RAM : 2 GB
Data transfer: Unlimited
Free setup
Cost | 50USD/month